CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Da Nang, Sep 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	11

1.3 Project Risks	14

2. Management Approach	18

2.1 Project Process	19

2.2 Quality Management	21

2.3 Training Plan	22

3. Project Deliverables	23

4. Responsibility Assignments	24

5. Project Communications	25

6. Configuration Management	26

6.1 Document Management	26

6.2 Source Code Management	26

6.3 Tools & Infrastructures	27

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 26/08/26 | A | KhoaNKD | Create Report2_Project Management Plan |
| 28/08/26 | A | VuNH | Added Section 3 - Project Deliverables and timeline. |
| 28/08/26 | A | HuyMD | Added Section 1.1 - Scope & Estimation |
| 28/08/26 | A | PhongTH | Added Section 5 - Project Communications |
| 28/08/26 | A | PhongTH | Added Section 6 - Configuration Management |
| 28/08/26 | M | KhoaNKD | Modify 6. Configuration Management |
| 28/08/26 | A | KhoaNKD | Added Section 2 - Management Approach |
| 28/08/26 | A | HuyMD | Added Section 1.2 - Project Objectives |
| 28/08/26 | A | HuyMD | Added Section 1.3 - Project Risks |
| 28/08/26 | A | HuyMD | Modify Section 1.2 - Project Objectives |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

#### 1.1.1 Effort Estimation Definition

Estimated Effort is the total work required to complete a work item, measured in man-days (MD). One man-day represents one team member working for one standard eight-hour day.

Estimated Effort (MD) = Total Estimated Person-Hours / 8

Effort represents workload, not calendar duration. For example, two members working for three days equals 6 man-days.

For software development items, the estimate includes requirement clarification, design, implementation, developer-level testing, bug fixing, and integration support. Project documentation, project-level testing, deployment, final reporting, and presentation preparation are estimated separately.

Work item complexity is classified as:

- Simple: Limited business logic and dependencies, typically 1–2 MD.

- Medium: Moderate business logic, user interaction, or integration, typically 2–3 MD.

- Complex: Advanced logic, real-time processing, concurrency, external integrations, or AI/ML, typically 3–5 MD.

Complexity is used as a relative indicator; the final effort depends on the actual technical requirements and dependencies.

#### 1.1.2 Project Capacity Assumption

The project is planned for approximately three months with a team of five members. Assuming approximately 60 working days during the project period:

Theoretical Project Capacity = Team Size × Planned Working Days

= 5 × 60

= 300 man-days

The planned WBS effort is 289 man-days, which accounts for approximately 96.3% of the theoretical project capacity. The remaining 11 man-days are reserved for unexpected rework, technical issues, minor requirement adjustments, or other unforeseen project activities.

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Project Management & Documentation |  | 29 |
| 1.1 | Report 1 – Project Introduction | Medium | 3 |
| 1.2 | Report 2 – Project Management Plan | Medium | 3 |
| 1.3 | Report 3 – Project Tracking | Medium | 2 |
| 1.4 | Report 3 – Software Requirement Specification | Complex | 5 |
| 1.5 | Report 4 – Software Design Document | Complex | 5 |
| 1.6 | Report 5 – Test Documentation | Medium | 3 |
| 1.7 | Report 5.1 – Unit Test Documentation | Medium | 2 |
| 1.8 | Report 5.2 – Integration Test Documentation | Medium | 2 |
| 1.9 | Report 5.3 – System Test Documentation | Medium | 2 |
| 1.10 | Report 6 – Software User Guides | Medium | 2 |
| 2 | Software Product Development |  | 236 |
| 2.1 | Authentication & Authorization |  | 17 |
| 2.1.1 | Account Registration & Email Verification | Complex | 4 |
| 2.1.2 | Login, Logout & Session Management | Medium | 3 |
| 2.1.3 | Google OAuth Login | Medium | 3 |
| 2.1.4 | Forgot, Reset & Change Password | Medium | 2 |
| 2.1.5 | Role-Based Access Control & Account Lock/Unlock | Complex | 3 |
| 2.1.6 | Two-Factor Authentication | Medium | 2 |
| 2.2 | User & Profile Management |  | 7 |
| 2.2.1 | View & Update User Profile and Avatar | Medium | 3 |
| 2.2.2 | Manage Workspace Preferences | Medium | 2 |
| 2.2.3 | User Detail, Status & Role Administration | Medium | 2 |
| 2.3 | Organizer Onboarding |  | 10 |
| 2.3.1 | Submit Organizer Application & Business Profile | Medium | 3 |
| 2.3.2 | Upload Verification Documents | Medium | 2 |
| 2.3.3 | Review, Approve & Reject Organizer Application | Complex | 3 |
| 2.3.4 | Application Status, Resubmission & Provider Suspension | Medium | 2 |
| 2.4 | Workspace Management |  | 10 |
| 2.4.1 | Workspace CRUD & Status Management | Complex | 3 |
| 2.4.2 | Configure Operating Hours & Workspace Policies | Medium | 2 |
| 2.4.3 | Google Maps Location Integration | Medium | 2 |
| 2.4.4 | Workspace Approval & Featured Workspace Management | Medium | 3 |
| 2.5 | Amenity, Facility & Media Management |  | 7 |
| 2.5.1 | Amenity Catalog & Workspace Amenity Assignment | Medium | 2 |
| 2.5.2 | Media Upload, Gallery, Cover Image & Deletion | Complex | 3 |
| 2.5.3 | 360° Workspace Preview (Option) | Medium | 2 |
| 2.6 | Floor Plan & Seat Management |  | 17 |
| 2.6.1 | Interactive Drag-and-Drop Floor Plan Editor | Complex | 5 |
| 2.6.2 | Seat/Room CRUD & Seat Type Configuration | Medium | 3 |
| 2.6.3 | Layout Coordinate Persistence & Clone Layout | Complex | 3 |
| 2.6.4 | Workspace Zones & Enable/Disable Seat | Medium | 2 |
| 2.6.5 | Zoom, Pan & Occupancy Visualization | Complex | 4 |
| 2.7 | Real-time Availability Management |  | 18 |
| 2.7.1 | Seat & Room Availability Query | Medium | 3 |
| 2.7.2 | Temporary Seat Hold & Automatic Release | Complex | 4 |
| 2.7.3 | Availability Synchronization & Double-booking Prevention | Complex | 5 |
| 2.7.4 | Real-time Availability UI Updates | Complex | 3 |
| 2.7.5 | Occupancy Calendar | Medium | 3 |
| 2.8 | Search & Discovery |  | 12 |
| 2.8.1 | Workspace Search | Medium | 3 |
| 2.8.2 | Location & Distance Filtering | Medium | 2 |
| 2.8.3 | Price, Amenity, Seat Type & Rating Filters and Sorting | Medium | 3 |
| 2.8.4 | Public Workspace Detail & Availability Preview | Medium | 2 |
| 2.8.5 | Search Suggestions & Saved Filters | Medium | 2 |
| 2.9 | Booking Management |  | 16 |
| 2.9.1 | Create Booking & Select Date/Seat/Room | Complex | 4 |
| 2.9.2 | Pending Payment Booking & Seat Hold Integration | Complex | 3 |
| 2.9.3 | Booking Detail & Booking History | Medium | 2 |
| 2.9.4 | Organizer Booking List, Calendar & Request Handling | Medium | 2 |
| 2.9.5 | Booking Lifecycle Management | Complex | 3 |
| 2.9.6 | Booking Audit, Invoice Access & Anomaly Flagging | Medium | 2 |
| 2.10 | Payment Management |  | 14 |
| 2.10.1 | Create PayOS Payment Request & Payment Link/QR | Complex | 3 |
| 2.10.2 | PayOS Webhook Handling & Signature Verification | Complex | 4 |
| 2.10.3 | Booking Update, Payment Failure & Expiry Handling | Medium | 3 |
| 2.10.4 | Payment History & Receipt Generation | Medium | 2 |
| 2.10.5 | Webhook Logging & Transaction Reconciliation | Medium | 2 |
| 2.11 | QR Check-in Management |  | 9 |
| 2.11.1 | Generate & Display Check-in QR | Medium | 2 |
| 2.11.2 | Scan & Validate QR | Complex | 3 |
| 2.11.3 | Check-in/out, Duplicate & Invalid QR Handling | Medium | 2 |
| 2.11.4 | Check-in/out History | Medium | 2 |
| 2.12 | Review & Rating Management |  | 6 |
| 2.12.1 | Review CRUD & Review Eligibility Validation | Medium | 2 |
| 2.12.2 | Review List & Average Rating Calculation | Medium | 2 |
| 2.12.3 | Organizer Reply, Report & Admin Moderation | Medium | 2 |
| 2.13 | Favorite Management |  | 3 |
| 2.13.1 | Add, Remove & Check Favorite Status | Simple | 2 |
| 2.13.2 | Favorite List & Workspace Grouping | Simple | 1 |
| 2.14 | Notification Management |  | 10 |
| 2.14.1 | Event-based Booking, Payment & Refund Notifications | Medium | 2 |
| 2.14.2 | In-app Notification Center & Read Status | Medium | 2 |
| 2.14.3 | Gmail/SMTP Email Notification | Medium | 2 |
| 2.14.4 | Booking Reminder Scheduler | Medium | 2 |
| 2.14.5 | Mobile Push Notification Integration | Medium | 2 |
| 2.15 | Membership & Pricing Management |  | 10 |
| 2.15.1 | Pricing Rules & Booking Price Calculation | Complex | 3 |
| 2.15.2 | Seat/Room Pricing Management | Simple | 1 |
| 2.15.3 | Membership Plan CRUD | Medium | 2 |
| 2.15.4 | Subscription & Subscriber Management | Medium | 2 |
| 2.15.5 | Discount & Platform Fee Management | Simple | 1 |
| 2.15.6 | Revenue by Membership Plan | Simple | 1 |
| 2.16 | Cancellation & Refund Management |  | 9 |
| 2.16.1 | Cancellation Policy & Booking Cancellation | Medium | 2 |
| 2.16.2 | Refund Request, Review, Approval & Rejection | Medium | 2 |
| 2.16.3 | Refund Amount Calculation & Payment Gateway Processing | Complex | 3 |
| 2.16.4 | Refund Status & Refund History | Medium | 2 |
| 2.17 | Admin Management |  | 8 |
| 2.17.1 | Reports, Complaints & Dispute Resolution | Medium | 2 |
| 2.17.2 | Platform Settings & Business Rules | Medium | 2 |
| 2.17.3 | Fees, Featured Workspace & Promotion Management | Medium | 2 |
| 2.17.4 | Audit Logs, Monitoring & Suspicious Activity Management | Medium | 2 |
| 2.18 | Analytics & Dashboard |  | 12 |
| 2.18.1 | Administrator Dashboard | Complex | 3 |
| 2.18.2 | Organizer Dashboard | Complex | 3 |
| 2.18.3 | Revenue, Booking & Occupancy Metrics | Medium | 2 |
| 2.18.4 | Growth, Cancellation, Peak Hour, Review & Transaction Analytics | Medium | 2 |
| 2.18.5 | Report Export | Medium | 2 |
| 2.19 | AI Workspace & Seat Recommendation |  | 16 |
| 2.19.1 | User Preference & Booking History Data Preparation | Medium | 3 |
| 2.19.2 | Recommendation Model & Scoring Engine | Complex | 4 |
| 2.19.3 | Workspace & Seat Recommendation API | Complex | 3 |
| 2.19.4 | Location, Budget, Seat Type & Similar Workspace Ranking | Medium | 3 |
| 2.19.5 | Recommendation Tracking & Model Evaluation | Complex | 3 |
| 2.20 | AI Chatbot Assistant |  | 10 |
| 2.20.1 | FAQ & Knowledge Base Preparation | Medium | 2 |
| 2.20.2 | LLM/AI Chat Service Integration | Medium | 2 |
| 2.20.3 | Workspace Search & Recommendation Tool Integration | Medium | 2 |
| 2.20.4 | Booking Guidance & Conversation Context Management | Medium | 2 |
| 2.20.5 | Chat History, Fallback Handling & Evaluation | Medium | 2 |
| 2.21 | Demand Forecasting |  | 8 |
| 2.21.1 | Historical Demand Data Preparation Pipeline | Medium | 2 |
| 2.21.2 | Forecasting Model Training & Evaluation | Complex | 3 |
| 2.21.3 | Forecast API & Dashboard Integration | Complex | 3 |
| 2.22 | No-show Prediction |  | 7 |
| 2.22.1 | Dataset Preparation, Labeling & Feature Engineering | Medium | 2 |
| 2.22.2 | Classification Model Training & Evaluation | Complex | 3 |
| 2.22.3 | Prediction API & Dashboard Integration | Medium | 2 |
| 3 | Project-level Testing & Quality Assurance |  | 10 |
| 3.1 | Integration Testing | Complex | 3 |
| 3.2 | System & End-to-End Testing | Complex | 3 |
| 3.3 | Performance & Concurrency Testing | Complex | 2 |
| 3.4 | Regression Testing & Defect Verification | Medium | 2 |
| 4 | Deployment & Production Preparation |  | 5 |
| 4.1 | Backend, AI Service & Database Deployment | Complex | 2 |
| 4.2 | Web Application Deployment | Medium | 1 |
| 4.3 | Mobile Release Build Preparation | Medium | 1 |
| 4.4 | Production Configuration & Deployment Verification | Medium | 1 |
| 5 | Final Documentation |  | 4 |
| 5.1 | Report 7 – Final Project Report | Complex | 4 |
| 6 | Final Presentation & Defense Preparation |  | 5 |
| 6.1 | Final Presentation Slide Preparation | Medium | 2 |
| 6.2 | Demo Scenario & Demo Data Preparation | Medium | 1 |
| 6.3 | Presentation Rehearsal & Timing | Medium | 1 |
| 6.4 | Final Defense & Q&A Preparation | Medium | 1 |
|  | Total Estimated Effort (man-days) |  | 289 |

Table II-1.1.2 Work Breakdown Structure and Effort Estimation

### 1.2 Project Objectives

#### 1.2.1 Overall Project Objective

NexSpace aims to develop a centralized Web and Mobile coworking space marketplace that connects Customers with independent and mid-sized coworking space Organizers. The platform provides an integrated solution for workspace discovery, interactive floor plan visualization, real-time seat and room availability, booking and reservation management, online payment through PayOS, QR-based check-in/check-out, reviews and ratings, favorites, notifications, membership and pricing management, cancellation and refund processing, and administrative management.

The system also incorporates AI-powered capabilities, including AI Workspace and Seat Recommendation, AI Chatbot Assistance, Demand Forecasting, and No-show Prediction. These features are intended to improve the Customer experience and support Organizers and Administrators in making more effective, data-driven workspace management decisions.

The project is planned to be completed within approximately three months by a team of five members. The Web application is prioritized as the primary platform, while the Mobile application focuses mainly on essential Customer functions. In addition to software implementation, the project scope includes required project documentation, testing activities, deployment, user guides, final reporting, demonstration preparation, and final defense activities.

The project aims to deliver a functional, secure, reliable, and maintainable system while maintaining project quality, meeting at least 90% of planned milestones on time, and controlling the total planned effort within 289 man-days.

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% of major project documents and critical designs | ≤ 15 | 30% | Review Project Introduction, PMP, SRS, SDD, test documentation, API specifications, database design, UI/UX designs, and major technical designs. |
| 2 | Unit Test | ≥ 80% coverage for critical business logic | ≤ 15 | 30% | Focus on authentication, booking, availability, payment, pricing, refund, check-in, notification, and AI-related logic. |
| 3 | Integration Test | 100% of critical integration scenarios | ≤ 10 | 20% | Verify integration among Web, Mobile, Backend, AI services, PayOS, Google OAuth, Google Maps, Gmail/SMTP, and cloud storage. |
| 4 | System Test | 100% of critical end-to-end business flows | ≤ 8 | 16% | Validate complete business processes under realistic system conditions. |
| 5 | Acceptance Test | 100% of mandatory acceptance scenarios | ≤ 2 | 4% | No unresolved Critical or High-severity defect is allowed before final acceptance. |

Table II-1.2.1 Project Quality Objectives

For this project, the % of Defect column represents the planned distribution of detected defects across the testing stages. The actual number of defects will be recorded and updated in the corresponding test documentation during project execution.

#### 1.2.2 Quality Target

The project shall achieve the following quality targets:

- 100% of major project documents and critical technical designs shall be reviewed.

- Critical business logic shall achieve at least 80% Unit Test coverage.

- 100% of critical integration and end-to-end scenarios shall be executed.

- All mandatory acceptance scenarios shall be tested.

- No unresolved Critical or High-severity defects shall remain before final project acceptance.

- Identified defects shall be recorded, tracked, retested, and closed through the project's defect management process.

#### 1.2.3 Milestone Timeliness (%)

Target: ≥ 90%

At least 90% of the planned project milestones shall be completed on or before their scheduled due dates. All mandatory Capstone deliverables, including project documents, software releases, testing results, deployment, user guides, final report, and presentation materials, must be completed before their official deadlines.

The milestone timeliness is calculated as:

Milestone Timeliness = Number of milestones completed on time​Total number of planned milestones×100%

Any milestone delayed by more than five working days shall require schedule reassessment, identification of the root cause, and corrective actions by the project team.

#### 1.2.4 Allocated Effort (man-days)

The total planned project effort is:

289 man−days​

The theoretical project capacity is approximately:

5 members×60 working days=300 man−days

Therefore:

Effort Utilization = 289300 ×100=96,3%

Approximately 11 man-days remain outside the planned baseline as schedule capacity for unexpected rework, technical problems, minor requirement adjustments, or short-term member unavailability.

#### 1.2.5 Allocated Effort by Project Activity

| # | Project Activity | Allocation | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Requirement Analysis | 11% | 32 |
| 2 | System & UI/UX Design | 14% | 40 |
| 3 | Coding & Integration | 53% | 153 |
| 4 | Testing & Bug Fixing | 13% | 38 |
| 5 | Project Management & Documentation | 6% | 17 |
| 6 | Deployment & Final Presentation | 3% | 9 |
|  | Total | 100% | 289 |

Table II-1.2.5 Allocated Effort by Project Activity

The total estimated project effort is 289 man-days. Approximately 11% is allocated to requirement analysis, 14% to system and UI/UX design, 53% to coding and integration, 13% to testing and defect resolution, 6% to project management and documentation, and 3% to deployment and final presentation activities.

The effort categories represent the type of work performed, rather than a direct mapping to the top-level WBS items. For example, preparation of the SRS contributes mainly to Requirement Analysis, the Software Design Document contributes mainly to Design, and Unit/Integration/System Test documentation contributes mainly to Testing.

This classification prevents the same effort from being counted twice.

#### 1.2.6 Effort Control Target

The project shall use 289 man-days as the approved effort baseline.

Actual project effort shall be reviewed regularly against the baseline. If the projected effort exceeds the available project capacity of approximately 300 man-days, the team shall reassess the remaining scope, prioritize mandatory functions, postpone non-critical enhancements, or formally revise the project plan.

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Team members may misunderstand or interpret project requirements differently, resulting in incorrect implementation or rework. | High | Medium | Clarify requirements before implementation, maintain detailed SRS and Use Case specifications, review requirements with the team, and confirm unclear requirements with the supervisor before development. |
| 2 | Miscommunication among team members may lead to inconsistent understanding of tasks, interfaces, priorities, or project status. | High | Medium | Conduct regular team meetings, maintain clear communication channels, record important decisions, update task status regularly, and confirm responsibilities after each meeting. |
| 3 | Project tasks or milestones may be completed later than planned, affecting subsequent activities and the final project deadline. | High | High | Define clear deadlines for each task, monitor progress weekly, identify delayed tasks early, redistribute workload when necessary, and prioritize critical project activities. |
| 4 | Poor time management or inaccurate effort estimation may cause the team to spend too much time on certain features while other important tasks remain unfinished. | High | Medium | Track actual effort against the WBS estimation, review remaining work regularly, limit unnecessary enhancements, and adjust task priorities based on project progress. |
| 5 | The project scope may increase during development because of new requirements, additional features, or changes requested after planning. | High | Medium | Apply scope and change control, evaluate the impact of each requested change on effort and schedule, prioritize mandatory requirements, and postpone low-priority enhancements when necessary. |
| 6 | Workload may be distributed unevenly among team members, causing some members to become overloaded while others have insufficient work. | Medium | Medium | Assign tasks based on workload and member capability, review task allocation regularly, redistribute tasks when imbalance occurs, and encourage members to support blocked or overloaded teammates. |
| 7 | A team member may become temporarily unavailable due to personal, academic, or unexpected reasons, delaying tasks assigned primarily to that member. | High | Medium | Avoid assigning critical knowledge to only one member, maintain updated documents and source code, perform regular knowledge sharing, and assign backup members for important modules. |
| 8 | Some team members may lack sufficient knowledge or experience to complete assigned tasks efficiently. | Medium | Medium | Identify skill gaps early, organize internal training and knowledge-sharing sessions, assign tasks according to member strengths, and use pair programming or technical support for difficult tasks. |
| 9 | Dependencies between team members or modules may block development when a prerequisite task is delayed or incomplete. | High | Medium | Identify dependencies during planning, define API contracts and interfaces early, prioritize prerequisite tasks, use mock data or temporary interfaces where possible, and monitor blocked tasks during project meetings. |
| 10 | Project documents may become outdated or inconsistent with the actual implemented system when changes are not updated across SRS, SDD, Test Documentation, User Guides, and other reports. | Medium | High | Assign document owners, update documents together with approved system changes, use document version control, and review all related documents at each project milestone. |
| 11 | Testing activities may be delayed or shortened because development tasks take longer than expected. | High | Medium | Prepare test cases early, perform Unit and Integration Testing continuously during development, define a feature-freeze milestone, and reserve sufficient time for System and Regression Testing before final delivery. |
| 12 | Source code changes from multiple members may cause merge conflicts, overwritten work, or unstable shared branches. | Medium | Medium | Define a Git branching and pull-request strategy, commit changes frequently, perform code reviews before merging, resolve conflicts early, and protect important branches from direct modification. |
| 13 | Important project decisions, task changes, or supervisor feedback may not be recorded properly, causing confusion or repeated discussion later. | Medium | Medium | Record meeting minutes and important decisions, maintain a shared project tracking document, assign responsible persons for follow-up actions, and review pending actions in subsequent meetings. |
| 14 | Project quality may decrease when the team prioritizes completing features over code review, testing, documentation, or defect fixing. | High | Medium | Define quality criteria for completed tasks, require code review and testing before task closure, track defects, and avoid marking features as completed until agreed acceptance criteria are satisfied. |
| 15 | Deployment and final system preparation may be delayed because development or testing is completed too close to the final deadline. | High | Medium | Prepare the deployment environment early, perform trial deployments before the final phase, maintain deployment instructions, and establish an internal deadline earlier than the official submission date. |
| 16 | Final reports, presentation slides, demo preparation, or rehearsal activities may receive insufficient time because the team focuses mainly on software development. | High | Medium | Prepare report structures and presentation outlines early, collect screenshots and project results continuously, finalize the demo scenario before the defense period, assign presentation responsibilities, and conduct rehearsal sessions before the final defense. |

Table II-1.3 Project Risks and Response Plans

## 2. Management Approach

[Describe the approach you would use the manage and implement your project]

To ensure the successful delivery of NexSpace within the constrained timeline (4 months) and budget, the project will be managed using the Agile Scrum framework.

1. Definition of the Framework

Agile Scrum is an iterative and incremental software development framework based on empirical process control. Instead of delivering the entire software at the very end of the project, Scrum breaks the development lifecycle into short, fixed-length iterations called Sprints (typically 2 weeks long). It relies on continuous feedback, self-organizing cross-functional teams, and regular delivery of working software pieces.

2. Why the Team Chose Agile Scrum

Given the strict 4-month academic deadline and the technical complexity of NexSpace, traditional linear methodologies (like Waterfall) pose a high risk. In Waterfall, testing and user feedback only occur at the final stages, making it costly and time-consuming to fix critical errors. The team chose Agile Scrum because it strictly mitigates this "late-discovery" risk. It allows the team to be highly adaptive to changes, validate requirements early, and ensure that at the end of every Sprint, a testable, functional segment of the software is completed.

3. Key Benefits for the Project

- Early Risk Mitigation: By developing in short sprints, technical bottlenecks (such as integrating the PayOS gateway or the AI Recommendation engine) can be identified and resolved early.

- Continuous Quality Assurance: Testing is integrated into every sprint rather than delayed to the end. This is crucial for verifying complex logic like the real-time seat availability and transaction locking mechanisms.

- High Adaptability: If stakeholders (Mentors/Supervisors) request UI/UX changes or feature modifications during sprint reviews, the team can easily adjust the Product Backlog for the next sprint without disrupting the entire project plan.

- Enhanced Team Collaboration: Daily Stand-up meetings ensure that all five team members remain synchronized, promptly removing blockers and maintaining project momentum.

4. How Agile Scrum Fits NexSpace

NexSpace is a multi-actor platform (Customer, Organizer, Admin) with both fundamental and advanced features. Scrum perfectly aligns with this structure through the concept of a Minimum Viable Product (MVP).

- In the early sprints, the team can focus purely on the core booking flow (Workspace Discovery → Booking → Payment).

- Once the core pipeline is stable and tested, subsequent sprints will incrementally introduce advanced features (Drag & Drop Floor Plan, AI Recommendations, QR Check-in). This phased, priority-driven approach guarantees that even if unexpected delays occur near the project deadline, the team will still possess a fully functional, deployable core application to present to the Capstone board.

### 2.1 Project Process

[Draw and describe the software development process model that the team would apply into the project implementation]

The team will apply the Agile Scrum Software Development Process Model. This iterative and incremental model is chosen over traditional Waterfall because it allows the team to quickly respond to feedback, adjust priorities, and deliver core features (such as interactive floor plans and real-time bookings) early in the project lifecycle.

Figure II-2.1: Agile Scrum Software Development Process for NexSpace.

The Scrum Process applied to NexSpace includes:

- Product Backlog: The Project Leader (acting as Product Owner) gathers all system requirements from the SRS document and creates a prioritized list of user stories and tasks (The Product Backlog).

- Sprint Planning: The project is divided into multiple 2-week Sprints. At the beginning of each sprint, the team selects high-priority tasks from the Product Backlog to form the Sprint Backlog.

- Sprint Execution: During the 2-week sprint, developers design, code, and test the selected features.

- Daily Scrum: The team holds brief daily meetings (Google Meet or offline) to synchronize activities, report progress, and identify any blockers.

- Sprint Review & Retrospective: At the end of each sprint, the team demonstrates the newly developed features to the Supervisor/Mentor for feedback, followed by an internal meeting to reflect on what went well and what needs improvement for the next sprint.

### 2.2 Quality Management

[Provide the approach you would apply to improve the project quality, reach the project quality objectives. Some of the quality approach can include

- Defect Prevention

- Reviewing

- Unit Testing

- Integration Testing

- System Testing

]

To reach the project's quality objectives—specifically minimizing defects, ensuring security in online payments, and preventing double-booking conflicts—the team will implement a comprehensive Quality Assurance (QA) strategy.

Figure II-2.2: Continuous Quality Management and Testing Pipeline.

The Quality Management approach includes:

- Defect Prevention:

  - Coding Standards: Enforcing strict naming conventions, architectural patterns (Clean Architecture), and RESTful API standards across the team.

  - Peer Reviewing / Code Review: Applying the Pull Request (PR) mechanism on GitHub. Before merging any code into the develop branch, at least one other team member must review the code for logic errors, security vulnerabilities, and adherence to coding standards.

- Testing Strategies:

  - Unit Testing: Developers must write unit tests for critical backend modules (e.g., pricing calculations, payment webhook handling, and AI recommendation engines) using JUnit (Java).

  - Integration Testing: Verifying that different modules work together smoothly, especially the interactions between the ReactJS/Flutter frontends and the Spring Boot backend APIs.

  - System & End-to-End Testing: Conducting holistic tests to validate complete user flows, such as the entire process from discovering a workspace, selecting a seat on the floor plan, checking out via PayOS, and receiving the check-in QR code.

  - Performance & Concurrency Testing: Simulating multiple users attempting to book the same seat simultaneously to guarantee the transaction locking mechanism functions perfectly and prevents double-booking.

### 2.3 Training Plan

[You need to plan the training activities in case any of your team member lack of knowledge/skills to handle the project works]

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Java Spring Boot & RESTful APIs | Backend Developers (All team members) | Week 1, 3 days | Mandatory for backend team; waived if the member has previous project experience. |
| Flutter & Dart (Mobile Dev) | Mobile Developers (All team members) | Week 2, 4 days | Mandatory for mobile team. |
| ReactJS & TypeScript | Frontend Developers (All team members) | Week 1, 3 days | Mandatory for frontend team. |
| Git, GitHub & CI/CD workflow | All team members | Week 1, 1 day | Mandatory for all members to ensure smooth collaboration. |
| PayOS Payment Integration | Backend & Frontend Leads | Week 4, 2 days | Mandatory for members assigned to the payment module. |
| Machine Learning / AI Integration | AI Feature Assigned Members | Week 6, 3 days | Mandatory for members handling the Recommendation and Demand Forecasting modules. |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | CAPSTONE PROJECT REGISTER | dd/MM/yyyy | Official project registration and initial project information. |
| 2 | Feature Analysis by Module | dd/MM/yyyy | Analyze and organize the main system features according to the Customer, Organizer, and Administrator modules. |
| 3 | Report1_Project Introduction | dd/MM/yyyy | Introduce the project background, problem statement, objectives, existing systems, software product vision, and proposed solution. |
| 4 | Report2_Project Management Plan | dd/MM/yyyy | Define the project management approach, project scope, schedule, resources, responsibilities, risks, and development plan. |
| 5 | Report3_Software Requirement Specification | dd/MM/yyyy | Specify the functional and non-functional requirements, system actors, use cases, business rules, and system requirements. |
| 6 | Report3_Project Tracking | dd/MM/yyyy | Track project progress, planned activities, actual progress, task completion, and project status. |
| 7 | Report4_Software Design Document | dd/MM/yyyy | Document the system architecture, software design, database design, component design, and technical solutions. |
| 8 | Report5_Test Documentation | dd/MM/yyyy | Define the testing strategy, test approach, test scope, test cases, testing procedures, and quality assurance activities. |
| 9 | Report5_Unit Test | dd/MM/yyyy | Implement and document unit tests for selected system components and verify individual functions. |
| 10 | Report5_Test Report | dd/MM/yyyy | Summarize testing results, defects, test execution status, and overall system quality evaluation. |
| 11 | Report6_Software User Guides | dd/MM/yyyy | Provide user instructions for using the main NexSpace functions. |
| 12 | Report7_Final Project Report | dd/MM/yyyy | Present the completed NexSpace system, development results, evaluation, limitations, conclusions, and future development directions. |
| 13 | Project Weekly Report_GroupName | dd/MM/yyyy | Record weekly project progress, completed tasks, ongoing activities, issues, and plans throughout the project. |

Table II-3  Project Deliverables

## 4. Responsibility Assignments

[Describe the main responsibilities in your project (to complete the outputs as defined in the above section), in the format as the sample below]

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | khoankdde180292 | huymdde180293 | vunhde180288 | hienhmde180291 | phongthde180299 |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | R | S | S | S |
| Prepare Project Introduction Document | R | D | S | S | S |
| Analyze System Features by User Module | S | R | D | D | S |
| Prepare Project Management Plan | D | S | S | R | S |
| Prepare SRS Document (Overview Part) | R | D | S | D | S |
| Prepare SRS Document (User Requirements) | S | R | D | D | S |
| Prepare SRS Document (Functional Requirements) | S | S | D | D | R |
| Prepare SRS Document (Non-functional Requirements) | D | S | R | S | D |
| Prepare Use Case Specifications | S | R | D | D | S |
| Prepare Software Design Document | S | S | R | D | D |
| Prepare System Architecture Design | S | S | R | R | D |
| Prepare Database Design | S | S | R | D | D |
| Prepare Test Documentation | S | S | R | R | D |
| Prepare Unit Test Cases | S | S | R | D | D |
| Execute Unit Testing | S | S | R | D | D |
| Prepare Test Report | R | S | S | D | D |
| Prepare Software User Guide | S | D | R | S | S |
| Prepare Final Project Report | D | R | R | R | R |
| Prepare Project Presentation & Demo | D | D | R | R | D |
| Prepare Weekly Project Progress Report | D | S | S | S | S |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily Meeting | All team members | Review daily progress & plan next steps. | Tue, Thu, Sat every week | Google meet |
| Weakly Meeting | All team members | Review last week's work, clear obstacles & plan for next week | Once a week (usually on Sunday evening ). | Google meet |
| Daily Working | All team members | Direct collaboration for quick task resolution & cross-functional support. | Mon, Wed, Fri every week | Offline |
| Meeting with Supervisor | All team members and mentors | Report progress, get feedback & align on technical requirements. | Once every 1-2 weeks (Usually depends on the mentor's availability). | Google meet |
| Unscheduled/ Urgent meeting | All team members | Address critical issues or sudden requirement changes. | As needed / On-demand (Whenever a critical issue arises). | Google meet |
| Messaging | All team members | Quick updates, file sharing, reminders & casual communication. | Daily, continuously. | Zalo |
| Document Storage | All team members | Centralize project docs, design files & source code for easy access. | Continuously updated whenever there is a new document or modification. | Google Drive, and GitHub |

Table II-5 Project Communications

## 6. Configuration Management

### 6.1 Document Management

- Document Rules:

  - Template: All documents must follow the FPT University template.

  - Cover Page: Every document must have a cover page with the FPT University logo. The Document Name and Project Name (NextSpace) must be big, clear, and in red text.

  - Structure: Use headings (Heading 1, Heading 2, Heading 3, etc.) to organize the content clearly. Every page must have a page number.

  - Font: Use the same font for all documents. The normal text size must be 11.

- Storage and Access:

  - Storage: We save all documents in a shared Google Drive folder.

  - Access: Only team members and mentors can open and read these documents.

- Document tool within project:

  - Google Docs

  - Google Sheets

  - Microsoft Office

### 6.2 Source Code Management

- Commit Criteria:

  - Commit Prefixes: Use the following prefixes to describe your action clearly:

    - feat: Used to indicate a commit for a new feature.

    - fix: Used when committing a change intended to resolve a bug in the system.

    - refactor: Used when modifying the code structure (e.g., splitting modules, renaming variables, or optimizing logic) to improve clarity without changing existing functionality.

  - Naming Format: Use the rule "Prefix: Task name" (Example: feat: Add user login).

  - Commit Rules:

    - Only commit when a task is fully completed. Avoid committing half-done or incomplete work.

    - Always test the code on your local machine. Ensure the code runs successfully without errors before making a commit.

- Branch Management:

  - Main Branches: We use two main branches: main (holds the stable, final code) and develop (holds the current working code).

  - Creating Branches: When starting a new task, team members must create a new sub-branch from the develop branch.

  - Branch Naming Convention: Name branches based on the task type. Format: type/task-name (Examples: feature/login-page, bugfix/payment-error).

  - Merging Rules: Team members cannot push code directly to main or develop. You must create a Pull Request (PR). At least one other team member must review and approve the PR before it is merged.

- Repository:

  - Storage: All project source code is stored in a private repository on GitHub (or GitLab).

  - Access: Only assigned team members and mentors have the right to view and edit the codebase.

- Source Code Structure:

  - Naming Convention: We follow standard coding rules (e.g., camelCase for variables and functions, PascalCase for classes and UI components).

  - Folder Convention: Folders are organized by features and technical layers (e.g., components, pages, services, assets). Folder names must be clear and written in lowercase.

  - Environment Variables: Security is a priority. Files containing sensitive API keys or database passwords (like .env) must never be pushed to the repository. They must be added to the .gitignore file. Instead, we upload a .env.example file as a template for other members to follow.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | ReactJS, TypeScript (FrontEnd), Flutter, Dart for Android and iOS (App), Java/SpringBoot (BackEnd) |
| Database | MySQL, FireBase |
| IDEs/Editors | Visual Studio Code, InteliJ,... |
| Diagramming | StarUML, DrawIO |
| Documentation | Ms Office, Google Docs/Sheets/Slides |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment server | Amazon Web Service |
| Project management | GitHub (Tasks, Defects) |

Table II-6.3 Tools & Infrastructures