## Summary & Legend
NEXSPACE CAPSTONE PROJECT - REPORT 3 TASK ASSIGNMENT
Software Requirement Specification (SRS) - Responsibility Matrix & Team Plan
RACI Legend
Code | Description | Role Definition
D | Do | Primary responsibility for executing and completing the task
R | Review | Evaluating, checking, and approving the final results
S | Support | Assisting the owner in performing the work items
I | Informed | Kept updated on progress and outcomes
Project Team Members
Full Name | Student ID | Assigned Focus Areas
Nguyễn Kim Đăng Khoa | khoankdde180292 | Project Leader, Architecture, ERD, Business Rules, Non-Screen Functions
Mai Đức Huy | huymdde180293 | Core Developer, Use Cases, Core Functional Modules (Booking, Payment, Floor Plan)
Nguyễn Hữu Vũ | vunhde180288 | Core Developer, UI/UX Flows, Screen Flow, Core Functional Modules
Hồ Minh Hiển | hienhmde180291 | QA & Developer, Authorization, Standard Features, Quality Attributes
Trương Hữu Phong | phongthde180299 | QA & Developer, Testing Docs, Common Requirements, Application Messages List

## SRS Responsibility Matrix
REPORT 3 (SRS) - RESPONSIBILITY ASSIGNMENT MATRIX (RACI)
Report 3 Section / Content Item | Nguyễn Kim Đăng Khoa (khoankdde180292) | Mai Đức Huy (huymdde180293) | Nguyễn Hữu Vũ (vunhde180288) | Hồ Minh Hiển (hienhmde180291) | Trương Hữu Phong (phongthde180299)
1. Overall Description
1.1 Product Overview (Context diagram) | D | R | S | I | I
2. User Requirements
2.1 System Actors | R | D | D | S | S
2.2 Use Cases (Diagrams & Descriptions) | R | D | D | S | S
3. Functional Requirements
3.1.1 & 3.1.2 Screens Flow & Screen Descriptions | I | S | D | S | R
3.1.3 Screen Authorization | R | I | I | D | S
3.1.4 Non-Screen Functions (Cron, APIs, AI) | D | R | S | I | I
3.1.5 Entity Relationship Diagram (ERD) | D | S | S | I | I
3.2 Core Feature Modules (Booking, Payment, Floor Plan) | R | D | D | S | S
3.y Standard Feature Modules (Auth, Profile, Review, Notif) | R | S | S | D | D
4. Non-Functional Requirements
4.1 External Interfaces (PayOS, Google Auth, Maps) | D | S | S | I | I
4.2 Quality Attributes (Usability, Reliability, Performance) | R | I | I | D | D
5. Requirement Appendix
1.2 & 5.1 Business Rules | D | R | R | S | S
5.2 Common Requirements | R | I | I | S | D
5.3 Application Messages List (Toast, Error msgs) | I | I | I | D | D